## Task Tracker
Remote Team Task Tracker & Status Handoff
Week of 13–19 Oct 2025 · Last updated: 19 Oct 2025
Task ID | Task | Owner | Priority | Status | Due | Dependency | Blocker / Note
T-101 | Finalize Q4 content calendar | Amina | High | In progress | 2025-10-17 | Brand guidelines from design | Waiting on final brand hex codes
T-102 | Clean CRM export for email list | Uthman | High | Done | 2025-10-15 |  | Delivered; 12 invalid emails flagged
T-103 | Draft onboarding email sequence (3) | Uthman | Medium | In progress | 2025-10-18 | T-102 list | Draft 1–2 ready; draft 3 in review
T-104 | Vendor invoice reconciliation | Uthman | High | Done | 2025-10-16 |  | Exceptions logged in shared sheet
T-105 | Research 5 competitor landing pages | Amina | Medium | Blocked | 2025-10-20 | Access to competitor archive | Need login to shared research folder
T-106 | Update help-center article: billing | Sam | Low | Not started | 2025-10-22 |  | —
T-107 | Prepare weekly status note for client | Uthman | High | Done | 2025-10-19 | T-101, T-103 | Sent 19 Oct 09:40 EAT
T-108 | Canva templates for social posts | Amina | Medium | In progress | 2025-10-21 | Brand guidelines | 3 of 6 templates complete
Handoff summary
Completed this week: CRM clean (T-102), invoice reconciliation (T-104), client status note (T-107).
In progress: content calendar (blocked on brand codes), email sequence drafts 1–2 ready, social templates 50%.
Needs attention: T-105 blocked on folder access; T-101 waiting on design tokens.
Next actions for manager: grant research-folder access; confirm brand hex codes by Wed.